## Legend & Instructions
Phoneme HR Suite — Requirement Traceability Register
Purpose: one living register linking Business objective -> Requirement -> Design/API/Screen reference -> Development item -> Test evidence -> Release, per module.
How to use:
- Each row is one requirement, identified by its Req ID (e.g. HR-M1-FR-006), matching the ID used in the BRD/PRD Feature List (Section 4.1/4.2).
- 'Design references (TDD)' cites the Technical Design Document section(s) that implement the requirement — keep this current as the TDD is revised.
- 'Test scenarios' should cover at minimum: a valid case, an invalid/edge case, an authorization/isolation case, and a concurrency/idempotency case where applicable — per the worked example for HR-M1-FR-006 in the original review.
- 'Status' values: Not started / In progress / Design complete / Test-ready. Update in place — do not delete or reorder rows as work progresses; historical status is tracked via the BRD/PRD and TDD Change Logs, not this register.
- 'Release evidence' is populated once a requirement is actually built and tested: build identifier, test run reference, and (for approval-gated requirements) the approval record.
- Add a new row for every new requirement ID as each module (3-10) reaches Approved Baseline in the BRD/PRD — one sheet per module, following the Module 1 / Module 2 pattern.
This register is the control referenced by BRD/PRD Section 5 (Acceptance Criteria, 'Traceability' row) and should be reviewed at every module baseline and before each release.

## Module 1
Phoneme HR Suite — Requirement Traceability Register — Module 1
Links: Business objective -> Requirement -> Design/API/Screen -> Development item -> Test evidence -> Release. Living document — update Status/Owner/Notes as each requirement progresses; do not delete rows on completion, update Status instead.
Req ID | Requirement | Business rule | Business objective | Design references (TDD) | Test scenarios | Release evidence | Status | Owner | Notes
HR-M1-FR-001 | Free-text brief ingestion (email + portal) | A manager's raw brief (email or portal) is converted to the structured JD Intake Schema; low-confidence fields are flagged for manager confirmation, never silently guessed. | Reduce time-to-hire | TDD Sec 6 (JobRequisition, JDBrief, JDField); TDD Sec 8 POST /api/v1/requisitions/intake | Valid brief via email; valid brief via portal; brief with unrecognized fields flagged; low-confidence field blocks freeze until confirmed | Build ID; test run; approval record | Design complete | Eng — Module 1
HR-M1-FR-002 | Multi-variant JD generation | System auto-generates 2-3 JD variants (formal, candidate-friendly, condensed) from structured data. | Reduce time-to-hire | TDD Sec 8 JD-versions endpoints; TDD Sec 12.1 steps 2-3 | 3 variants generated on valid structured input; regeneration on manager-requested changes | Build ID; test run; approval record | Design complete | Eng — Module 1
HR-M1-FR-003 | Email + portal review loop | Manager approves/edits via direct email reply (NLP-parsed) or in-portal editor; both converge on the same draft. | Reduce time-to-hire | TDD Sec 8 feedback POST; TDD Sec 12.1 steps 5-6 | Email reply parsed correctly; portal edit applied correctly; low-confidence parse routes to portal confirmation | Build ID; test run | Design complete | Eng — Module 1
HR-M1-FR-004 | JD versioning & audit trail | Every edit stored as a version with author/timestamp; an Approved version is immutable and only ever superseded, never overwritten. | Reduce compliance risk | TDD Sec 6 JDVersion (status enum, superseded_by); TDD Sec 15 error-handling rows | Edit to Approved version rejected (409); new version created via standard flow; Superseded version remains readable; DB-level immutability constraint holds under direct write attempt | Build ID; test run; migration/constraint verification | Design complete | Eng — Module 1
HR-M1-FR-005 | Approval SLA & escalation | Configurable reminder/escalation timer if a manager doesn't respond to a pending JD. | Reduce time-to-hire | TDD Sec 14 SLA escalation bullet; TDD Sec 12.1 step 7 | Reminder fires at configured threshold; HR escalation fires if still unresolved; scheduled-job (not request-time) verified under a stalled request | Build ID; test run | Design complete | Eng — Module 1
HR-M1-FR-006 | Draft-then-freeze weighted scoring matrix | Manager confirms valid scoring weights before JD publication; permitted weights total 100%; unresolved required fields block approval. | Reduce time-to-hire; create a defensible data moat | TDD Sec 6 ScoringMatrix/ScoringCriterion (jd_version_id-keyed); TDD Sec 8 draft-matrix GET/PATCH + freeze POST; TDD Sec 12.1 steps 5,8-9 | Valid approval (weights=100%); invalid total rejected (409); unauthorized user blocked; simultaneous freeze attempts — exactly one succeeds; repeated freeze request is a no-op | Build ID; test run; approval record | Design complete | Eng — Module 1 | Reviewer's own worked example requirement — see review notes
HR-M1-FR-007 | Staffing-agency / multi-client requisitions | An agency-tenant requisition is raised against a specific end-client company; a direct-employer tenant has no client selection. | Land-and-expand within accounts | TDD Sec 5 Tenant & Organization Model; TDD Sec 5.3 Isolation Enforcement Matrix; TDD Sec 15 (agency requisition without client_id row) | Agency requisition without client_id rejected (422); direct-employer requisition with client_id rejected/ignored per design; cross-client isolation test | Build ID; test run; isolation-test suite run | Design complete | Eng — Module 1 | Release 1 in-scope per business decision
HR-M1-FR-008 | JD templates | Save an Approved JD + matrix as a reusable template for recurring roles. | Reduce time-to-hire | Not yet in TDD v2.0 — Should-have, deferred design | Not yet defined | Not started | Not started | Eng — Module 1 | Should-have; design pending

## Module 2
Phoneme HR Suite — Requirement Traceability Register — Module 2
Links: Business objective -> Requirement -> Design/API/Screen -> Development item -> Test evidence -> Release. Living document — update Status/Owner/Notes as each requirement progresses; do not delete rows on completion, update Status instead.
Req ID | Requirement | Business rule | Business objective | Design references (TDD) | Test scenarios | Release evidence | Status | Owner | Notes
HR-M2-FR-001 | Multi-channel job posting | Publish an Approved requisition to careers page and contracted job-board integrations from one action. | Reduce time-to-hire | TDD Sec 9 publish endpoint; TDD Sec 12.2 step 1 | Publish fans out to all active configured channels; publish fails gracefully if one channel is in Integration Error | Build ID; test run | Design complete | Eng — Module 2
HR-M2-FR-002 | Job-board API integration (not scraping) | Sourcing channels ship only via official, contracted API/RMS integrations, direct email intake, or manual upload — never scraping. | Reduce compliance risk | TDD Sec 10.1-10.2 (status: proposed adapter contract, pending vendor confirmation) | Vendor auth flow succeeds; vendor product-tier confirmed (gate); rate-limit/backoff behavior verified | Vendor confirmation record; build ID; test run | Not started | Eng — Module 2 | Blocked on vendor/product-tier confirmation — Section 6 of BRD/PRD
HR-M2-FR-003 | Email intake parsing | Dedicated per-(tenant, client) inbox auto-parses incoming resumes/attachments. | Reduce time-to-hire | TDD Sec 10.3 Email Intake; TDD Sec 9 email webhook | Attachment correctly extracted and routed to Resume Parsing; body retained for audit but not parsed for structured fields | Build ID; test run | Design complete | Eng — Module 2
HR-M2-FR-004 | Resume parsing (PDF/DOCX only, Release 1) | Extract structured fields (contact, experience, skills, education) from PDF/DOCX resumes only; other formats rejected at intake, not silently dropped. | Reduce time-to-hire; create a defensible data moat | TDD Sec 10.4 Resume Parsing Service | Valid PDF parses; valid DOCX parses; unsupported format (.doc/.rtf/image) rejected with explicit error; scanned/password-protected PDF routed to manual fallback | Build ID; test run | Design complete | Eng — Module 2 | Corrects earlier 'any resume format' claim
HR-M2-FR-005 | Unified resume inbox | One consolidated view across all channels, scoped to (tenant, client), instead of separate per-source screens. | Reduce time-to-hire | TDD Sec 9 candidates search endpoint; TDD Sec 5.3 isolation matrix (search/index row) | Search results limited to caller's (tenant, client) scope; client resolved server-side, never caller-supplied | Build ID; test run; isolation-test suite run | Design complete | Eng — Module 2
HR-M2-FR-006 | Duplicate detection with conflict handling | Flag likely-duplicate candidates on intake and link rather than duplicate; conflicting evidence routes to manual review; every resolution retained for audit and may be reversed non-destructively. | Create a defensible data moat; reduce compliance risk | TDD Sec 7.1 DuplicateMatch (resolution/conflict_flag); TDD Sec 14 dedupe matching order; TDD Sec 15 (conflicting-evidence, reversal rows) | Exact email/phone match auto-links; conflicting evidence routes to pending+conflict_flag; recruiter reversal is non-destructive and audited; false-positive marked rejected_not_duplicate | Build ID; test run; audit-log verification | Design complete | Eng — Module 2
HR-M2-FR-007 | Candidate database search | Full-text and filtered search across the caller's (tenant, client)-scoped candidate pool. | Reduce time-to-hire | TDD Sec 9 candidates search endpoint | Full-text query returns expected matches; filters combine correctly; cross-tenant/cross-client leakage test | Build ID; test run; isolation-test suite run | Design complete | Eng — Module 2
HR-M2-FR-008 | Referral capture & attribution | Referral link/form tied to the referring employee, captured at intake. | Reduce time-to-hire | Not yet in TDD v2.0 — Should-have, deferred design | Not yet defined | Not started | Not started | Eng — Module 2 | Should-have; design pending