## Legend & Instructions
Phoneme HR Suite — Requirement Traceability Register
Purpose: one living register linking Business objective -> Requirement -> Design/API/Screen reference -> Dev item -> Test evidence -> Release, per module, plus a dedicated Platform & NFR sheet for cross-cutting non-functional requirements.
How to use:
- Each row is one requirement, identified by its Req ID (e.g. HR-M1-FR-006), matching the ID used in the BRD/PRD Feature List (Section 4.1/4.2), or an HR-NFR-xxx ID on the Platform & NFR sheet.
- 'Design references (TDD v2.1)' cites the Technical Design Document section(s) that implement the requirement — keep this current as the TDD is revised; update the version noted in the column header when the TDD reaches its next version.
- 'Dev item / backlog ref' and 'UX reference' are left blank until an actual backlog item / screen or prototype exists — populate them when they are created, never with a placeholder.
- 'Test IDs & scenarios': each requirement's test cases are individually numbered (TC-<module>-<req seq>-<nn>) so they can be referenced from a test-management tool later; at minimum cover a valid case, an invalid/edge case, an authorization/isolation case, and a concurrency/idempotency case where applicable.
- 'Test execution status' (Not run / Pass / Fail / N/A - design stage) is tracked separately from 'Design status' — a requirement can be Design complete with all tests still Not run; these two columns must never be conflated.
- 'Target release' and 'Release commitment' (Committed / Deferred / TBD) are independent of Priority (Must-have/Should-have) in the BRD/PRD — priority says how important a feature is, release commitment says whether it is actually going into a specific release.
- 'Design status' values: Not started / Blocked / In progress / Design complete. The gate for Design complete: every open question the original specification review raised against that requirement's design has an explicit, current resolution in the TDD/BRD-PRD — not merely that a design section exists. A requirement blocked on an external dependency (e.g. vendor confirmation) is Blocked, not Design complete, even if the rest of its design is finished.
- 'Release evidence' is populated only once a requirement is actually built and tested: build identifier, test run reference, and (for approval-gated requirements) the approval record. Leave it blank rather than writing placeholder text — a populated-looking cell should mean real evidence exists.
- Add a new row for every new requirement ID as each module (3-10) reaches Approved Baseline in the BRD/PRD — one sheet per module, following the Module 1 / Module 2 pattern. Add new HR-NFR-xxx rows to the Platform & NFR sheet as new cross-cutting requirements are identified.
- Never delete or reorder existing rows; use the Register Change History sheet to record what changed and why at each register revision, since the BRD/PRD and TDD change logs track document-level changes, not row-level register changes.
This register is the control referenced by BRD/PRD Section 5 (Acceptance Criteria, 'Traceability' row) and should be reviewed at every module baseline and before each release.

## Module 1
Phoneme HR Suite — Requirement Traceability Register — Module 1
Links: Business objective -> Requirement -> Design/API/Screen -> Dev item -> Test evidence -> Release. Living document — update Design status / Test execution status / Owner / Notes as work progresses; never delete or reorder rows, and never write a value into Release evidence until it actually exists.
Req ID | Requirement | Business rule | Business objective | Design references (TDD v2.1) | Dev item / backlog ref | UX reference | Test IDs & scenarios | Test execution status | Target release | Release commitment | Release evidence | Design status | Owner | Notes
HR-M1-FR-001 | Free-text brief ingestion (email + portal) | A manager's raw brief (email or portal) is converted to the structured JD Intake Schema; low-confidence fields are flagged for manager confirmation, never silently guessed. | Reduce time-to-hire | TDD Sec 6 (JobRequisition, JDBrief, JDField); TDD Sec 8 POST /api/v1/requisitions/intake |  |  | TC-M1-001-01 valid brief via email; TC-M1-001-02 valid brief via portal; TC-M1-001-03 brief with an unrecognized field flagged low-confidence; TC-M1-001-04 low-confidence field blocks freeze until confirmed | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1
HR-M1-FR-002 | Multi-variant JD generation | System auto-generates 2-3 JD variants (formal, candidate-friendly, condensed) from structured data. | Reduce time-to-hire | TDD Sec 8 JD-versions endpoints; TDD Sec 12.1 steps 2-3 |  |  | TC-M1-002-01 3 variants generated on valid structured input; TC-M1-002-02 regeneration on manager-requested changes produces a new Draft/Revising version, not an in-place edit | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1
HR-M1-FR-003 | Email + portal review loop | Manager approves/edits via direct email reply (NLP-parsed) or in-portal editor; both converge on the same draft. | Reduce time-to-hire | TDD Sec 8 feedback POST; TDD Sec 12.1 steps 5-6 |  |  | TC-M1-003-01 email reply parsed correctly; TC-M1-003-02 portal edit applied correctly; TC-M1-003-03 low-confidence parse routes to portal confirmation rather than auto-applying | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1
HR-M1-FR-004 | JD versioning & audit trail | Every edit stored as a version with author/timestamp; an Approved version is immutable and only ever superseded, never overwritten. | Reduce compliance risk | TDD Sec 6.0 (state table), Sec 6 JDVersion (status enum incl. Revising, superseded_by, immutability exception), Sec 15 |  |  | TC-M1-004-01 edit to Approved version rejected (409); TC-M1-004-02 new version created via standard flow; TC-M1-004-03 Superseded version remains readable by ID; TC-M1-004-04 DB-level trigger blocks a direct content-field UPDATE on an Approved row; TC-M1-004-05 the trigger allows only the status/superseded_by supersession write | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1 | Immutability-exception scope fixed in TDD v2.1 Section 6
HR-M1-FR-005 | Approval SLA & escalation | Configurable reminder/escalation timer if a manager doesn't respond to a pending JD. | Reduce time-to-hire | TDD Sec 14 SLA escalation bullet; TDD Sec 12.1 step 7 |  |  | TC-M1-005-01 reminder fires at configured threshold; TC-M1-005-02 HR escalation fires if still unresolved; TC-M1-005-03 scheduled-job behavior verified under a stalled request (not a request-time check) | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1
HR-M1-FR-006 | Draft-then-freeze weighted scoring matrix | Manager confirms valid scoring weights before JD publication; permitted weights total 100%; unresolved required fields block approval. | Reduce time-to-hire; create a defensible data moat | TDD Sec 6 ScoringMatrix/ScoringCriterion (jd_version_id-keyed); TDD Sec 8 draft-matrix GET/PATCH (versioned, revision-checked) + freeze POST (expected_active_version_id idempotency table) |  |  | TC-M1-006-01 valid approval (weights=100%); TC-M1-006-02 invalid total rejected (409); TC-M1-006-03 unauthorized user blocked; TC-M1-006-04 two simultaneous freeze attempts — exactly one succeeds per the expected_active_version_id table, the other gets 409 stale_expected_version; TC-M1-006-05 exact-repeat freeze request is a 200 no-op, not a 409; TC-M1-006-06 concurrent draft-matrix PATCHes — the stale one is rejected on matrix_revision mismatch | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1 | Freeze idempotency/concurrency and draft-matrix version-scoping resolved in TDD v2.1 Section 8
HR-M1-FR-007 | Staffing-agency / multi-client requisitions | An agency-tenant requisition is raised against a specific end-client company; a direct-employer tenant has no client selection. | Land-and-expand within accounts | TDD Sec 5 Tenant & Organization Model (incl. RLS + storage-credential scoping); TDD Sec 5.2 explicit-null-vs-absent rule; TDD Sec 15 |  |  | TC-M1-007-01 agency requisition without client_id rejected (422); TC-M1-007-02 direct-employer requisition WITH a client_id supplied rejected (422) — corrected in v2.1, was previously ambiguous; TC-M1-007-03 cross-client isolation test (one client's data never visible to another under the same agency); TC-M1-007-04 raw-SQL/background-job connection with no session tenant context returns zero rows under RLS | Not run | Release 1 | Committed |  | Design complete | Eng — Module 1 | Direct-employer client_id handling corrected to match TDD (422, not silently ignored) — BRD/PRD v2.1 and register both updated
HR-M1-FR-008 | JD templates | Save an Approved JD + matrix as a reusable template for recurring roles. | Reduce time-to-hire | Not yet in TDD — Should-have, design not started |  |  | Not yet defined | N/A - design stage | Fast-follow | Deferred |  | Not started | Eng — Module 1 | Should-have; no TDD content yet

## Module 2
Phoneme HR Suite — Requirement Traceability Register — Module 2
Links: Business objective -> Requirement -> Design/API/Screen -> Dev item -> Test evidence -> Release. Living document — update Design status / Test execution status / Owner / Notes as work progresses; never delete or reorder rows, and never write a value into Release evidence until it actually exists.
Req ID | Requirement | Business rule | Business objective | Design references (TDD v2.1) | Dev item / backlog ref | UX reference | Test IDs & scenarios | Test execution status | Target release | Release commitment | Release evidence | Design status | Owner | Notes
HR-M2-FR-001 | Multi-channel job posting | Publish an Approved requisition to careers page and contracted job-board integrations from one action. | Reduce time-to-hire | TDD Sec 9 publish endpoint; TDD Sec 12.2 step 1 |  |  | TC-M2-001-01 publish fans out to all active configured channels; TC-M2-001-02 publish continues for other channels when one is in Integration Error; TC-M2-001-03 agency requisition uses the correct end-client's own channel credentials, not another client's | Not run | Release 1 | Committed |  | Design complete | Eng — Module 2
HR-M2-FR-002 | Job-board API integration (not scraping) | Sourcing channels ship only via official, contracted API/RMS integrations, direct email intake, or manual upload — never scraping. | Reduce compliance risk | TDD Sec 10.1-10.2 (status: proposed adapter contract, pending vendor confirmation) |  |  | TC-M2-002-01 vendor auth flow succeeds once contracted; TC-M2-002-02 vendor product-tier confirmed (gate, blocking); TC-M2-002-03 rate-limit/backoff behavior verified | N/A - design stage | Release 1 | Committed |  | Blocked | Eng — Module 2 | Blocked on vendor/product-tier confirmation — BRD/PRD Section 6 dependency; design cannot reach complete until the vendor gate clears
HR-M2-FR-003 | Email intake parsing | Dedicated per-(tenant, client) inbox auto-parses incoming resumes/attachments. | Reduce time-to-hire | TDD Sec 10.3 Email Intake; TDD Sec 9 email webhook |  |  | TC-M2-003-01 attachment correctly extracted and routed to Resume Parsing; TC-M2-003-02 body retained for audit but not parsed for structured fields; TC-M2-003-03 email with no attachment creates no Candidate/Application record | Not run | Release 1 | Committed |  | Design complete | Eng — Module 2
HR-M2-FR-004 | Resume parsing (PDF/DOCX only, Release 1) | Extract structured fields (contact, experience, skills, education) from PDF/DOCX resumes only; other formats rejected at intake, not silently dropped. | Reduce time-to-hire; create a defensible data moat | TDD Sec 10.4 Resume Parsing Service |  |  | TC-M2-004-01 valid PDF parses; TC-M2-004-02 valid DOCX parses; TC-M2-004-03 unsupported format (.doc/.rtf/image) rejected with explicit error; TC-M2-004-04 scanned/password-protected PDF routed to manual fallback; TC-M2-004-05 parse-accuracy sample measured against the provisional BRD/PRD Section 5 target | Not run | Release 1 | Committed |  | Design complete | Eng — Module 2 | Corrects earlier 'any resume format' claim
HR-M2-FR-005 | Unified resume inbox | One consolidated view across all channels, scoped to (tenant, client), instead of separate per-source screens. | Reduce time-to-hire | TDD Sec 9 candidates search endpoint; TDD Sec 5.3 isolation matrix (search/index row) |  |  | TC-M2-005-01 search results limited to caller's (tenant, client) scope; TC-M2-005-02 client resolved server-side, never accepted as caller-supplied filter | Not run | Release 1 | Committed |  | Design complete | Eng — Module 2
HR-M2-FR-006 | Duplicate detection with conflict handling | Flag likely-duplicate candidates on intake and link rather than duplicate; conflicting evidence routes to manual review; every resolution retained for audit and may be reversed non-destructively. | Create a defensible data moat; reduce compliance risk | TDD Sec 7.1 DuplicateMatch (resolution/conflict_flag/previous_decision_id, append-only model); TDD Sec 14 dedupe matching order; TDD Sec 15 |  |  | TC-M2-006-01 exact email/phone match auto-links; TC-M2-006-02 conflicting evidence routes to pending+conflict_flag; TC-M2-006-03 recruiter reversal inserts a new row (previous_decision_id set), original row unmodified; TC-M2-006-04 current-link state correctly resolves to the latest row by resolved_at, not an arbitrary row; TC-M2-006-05 false-positive marked rejected_not_duplicate with resolution_notes | Not run | Release 1 | Committed |  | Design complete | Eng — Module 2 | Append-only reversal model made consistent across TDD Sec 7.1/15 in v2.1 (previously contradictory)
HR-M2-FR-007 | Candidate database search | Full-text and filtered search across the caller's (tenant, client)-scoped candidate pool. | Reduce time-to-hire | TDD Sec 9 candidates search endpoint |  |  | TC-M2-007-01 full-text query returns expected matches; TC-M2-007-02 filters combine correctly; TC-M2-007-03 cross-tenant/cross-client leakage test; TC-M2-007-04 filter by an unauthorized requisition returns no results, not an error leaking existence; TC-M2-007-05 p95 latency measured against the provisional BRD/PRD Section 5 target | Not run | Release 1 | Committed |  | Design complete | Eng — Module 2
HR-M2-FR-008 | Referral capture & attribution | Referral link/form tied to the referring employee, captured at intake. | Reduce time-to-hire | Not yet in TDD — Should-have, design not started |  |  | Not yet defined | N/A - design stage | Fast-follow | Deferred |  | Not started | Eng — Module 2 | Should-have; no TDD content yet

## Platform & NFR
Phoneme HR Suite — Requirement Traceability Register — Platform & NFR
Links: Business objective -> Requirement -> Design/API/Screen -> Dev item -> Test evidence -> Release. Living document — update Design status / Test execution status / Owner / Notes as work progresses; never delete or reorder rows, and never write a value into Release evidence until it actually exists.
Req ID | Requirement | Business rule | Business objective | Design references (TDD v2.1) | Dev item / backlog ref | UX reference | Test IDs & scenarios | Test execution status | Target release | Release commitment | Release evidence | Design status | Owner | Notes
HR-NFR-ISO-001 | Tenant data isolation | No cross-tenant data access, enforced at database (RLS + query-builder), message-queue, search-index, object-storage, and webhook layers — not schema convention alone. | Reduce compliance risk; trust | TDD Sec 5.3 Isolation Enforcement Matrix |  |  | TC-NFR-ISO-001-01 automated cross-tenant isolation suite across all 5 layers; TC-NFR-ISO-001-02 raw-SQL connection with no session context returns zero rows under RLS | Not run | Release 1 | Committed |  | Design complete | Eng — Platform | BRD/PRD Sec 5 'Data isolation (tenant)' criterion
HR-NFR-ISO-002 | Agency client data isolation | Within one agency tenant, no cross-client data access — a user scoped to one client never sees another client's requisitions or candidates. | Reduce compliance risk; land-and-expand trust | TDD Sec 5.2-5.3 |  |  | TC-NFR-ISO-002-01 cross-client isolation suite; TC-NFR-ISO-002-02 Client Stakeholder role explicitly has zero access in Release 1 (role does not exist) | Not run | Release 1 | Committed |  | Design complete | Eng — Platform | BRD/PRD Sec 5 'Data isolation (agency client)' criterion
HR-NFR-SEC-001 | Encryption at rest and in transit | PII and credentials encrypted at rest via envelope encryption (KMS + per-tenant DEK); TLS in transit. | Reduce compliance risk | TDD Sec 4.1-4.2 Key Management |  |  | TC-NFR-SEC-001-01 column-level encryption verified on PII fields; TC-NFR-SEC-001-02 object storage SSE-KMS verified; TC-NFR-SEC-001-03 no plaintext secret in any service's long-lived config | Not run | Release 1 | Committed |  | Design complete | Eng — Platform
HR-NFR-SEC-002 | Key rotation and re-encryption | DEK rotation every 90 days; KMS master-key rotation per provider default; re-encryption of existing data is a separate, explicitly scheduled, resumable job. | Reduce compliance risk | TDD Sec 4.2 (corrected master-key-rotation behavior, v2.1) |  |  | TC-NFR-SEC-002-01 DEK version rotates on schedule; TC-NFR-SEC-002-02 master-key rotation does not break decrypt of existing DEKs; TC-NFR-SEC-002-03 interrupted re-encryption job resumes from its watermark without data loss or duplication | Not run | Release 1 | Committed |  | Design complete | Eng — Platform | Master-key-rotation description corrected in TDD v2.1 to match AWS KMS behavior
HR-NFR-SEC-003 | Audit logging | Every secret access and every candidate-PII access is logged with requester identity, tenant_id, and purpose. | Reduce compliance risk | TDD Sec 4.2; Sec 3.2 field-level authorization |  |  | TC-NFR-SEC-003-01 secret access produces an audit-log entry; TC-NFR-SEC-003-02 candidate-PII read produces an audit-log entry | Not run | Release 1 | Committed |  | Design complete | Eng — Platform | BRD/PRD Sec 5 'Security' criterion
HR-NFR-PERF-001 | Candidate search performance | p95 query latency within a stated target at a reference data volume and concurrency. | Reduce time-to-hire (usability) | Not yet in TDD — target stated in BRD/PRD Sec 5, provisional pending Product/Eng sign-off |  |  | TC-NFR-PERF-001-01 load test at reference volume/concurrency measured against the provisional target | N/A - design stage | Release 1 | TBD |  | In progress | Eng — Platform | Provisional target only; needs Product/Eng sign-off per BRD/PRD Sec 6 dependency
HR-NFR-PERF-002 | Resume upload limits | Single-file and bulk-upload size/count limits are enforced and documented. | Predictable system behavior | Not yet in TDD — target stated in BRD/PRD Sec 5, provisional pending Product/Eng sign-off |  |  | TC-NFR-PERF-002-01 upload at/above the limit is rejected with a clear error, not a silent truncation or timeout | N/A - design stage | Release 1 | TBD |  | In progress | Eng — Platform | Provisional target only; needs Product/Eng sign-off
HR-NFR-REC-001 | Availability and recovery (RPO/RTO) | Stated monthly availability target; Recovery Point/Time Objectives for the primary datastore. | Trust; business continuity | Not yet in TDD — target stated in BRD/PRD Sec 5, provisional pending Product/Eng sign-off; full operational/DR design is a Section 8 roadmap deliverable |  |  | TC-NFR-REC-001-01 backup/restore drill measured against the provisional RPO/RTO | N/A - design stage | Release 1 | TBD |  | Not started | Eng — Platform / SRE | Operational/DR detail intentionally out of TDD v2.1 scope — tracked here so it isn't lost
HR-NFR-DUP-001 | Duplicate-detection precision | False-positive auto-link rate held to a stated target, measured on a labeled sample. | Trust; data quality | TDD Sec 7.1, Sec 14; target in BRD/PRD Sec 5 (provisional) |  |  | TC-NFR-DUP-001-01 quarterly measurement against the provisional target using resolved DuplicateMatch decisions | N/A - design stage | Release 1 | TBD |  | In progress | Eng — Module 2 | Design (the append-only decision model) is complete; the numeric target itself is still provisional

## Register Change History
Requirement Traceability Register — Change History
Version | Date | Change summary
1.0 | 15-Sep-2026 | Initial register: 16 functional requirement IDs (Module 1 + Module 2), seeded from BRD/PRD v2.0 and TDD v2.0.
1.1 | 15-Sep-2026 | Second-pass revision: added Dev item/backlog reference and UX reference columns (currently blank, pending assignment); split Test scenarios into individually-numbered Test IDs with a separate Test execution status column; added Target release and Release commitment (Committed/Deferred/TBD) columns — Should-have items HR-M1-FR-008 and HR-M2-FR-008 marked Deferred/Fast-follow, all Must-haves marked Committed/Release 1 pending the two vendor/target gates noted; reclassified Design status per an explicit design-complete gate (resolved vs. merely-drafted) rather than marking everything Design complete by default — HR-M2-FR-002 moved to Blocked (vendor gate), three new Platform/NFR performance/recovery rows moved to In progress or Not started pending target sign-off; added data-validation dropdowns for Design status, Release commitment, and Test execution status; fixed the HR-M1-FR-007 direct-employer-client_id wording to match the corrected TDD (422 rejection, not 'rejected/ignored'); added the Platform & NFR sheet (isolation, security, performance, recovery, duplicate-precision) so non-functional requirements are tracked with IDs, not left implicit; left Release evidence blank everywhere — no requirement has shipped yet — with instructions moved to the legend; added this Change History sheet, since row-level history is not otherwise captured by the BRD/PRD or TDD change logs.